## Slide 1
Testing Phase

## Slide 2: Phase 1: Chatbot Interface
Users:
  30 Burger Burger employees/internal stakeholders
  30 friends
Features Tested:
  Menu system
  Ordering/customization process
  Order confirmation & payment
Process:
  Each user makes 3 orders with fake Stripe credit card info
  20 people stress test the bot by messaging the bot at the same time w/ orders
User Interviews & Feedback:
  User interview with every single user on UI feedback conducted after product usage
Days : 1-4
Projected Date: Oct.18 - 21

## Slide 3: Phase 2: Cashier View & Kitchen Pick-Up
Users:
  30 Burger Burger employees/internal stakeholders
Features Tested:
  Orders for pick-up
  Cashier view web application on laptop
  Restaurant process
Process:
  Each user one order with real Stripe credit card info
  Monitor how efficient cashiers are inputting orders and delivering orders to the kitchen by timing their speed
User Interviews & Feedback:
  User interview with cashier and cooks conducted daily after product usage
Days : 5-9
Projected Date: Oct.22 - 26

## Slide 4: Phase 3: Delivery
Users:
  30 Burger Burger employees/internal stakeholders
Features Tested:
  Delivery system
Process:
  Each user one order with real Stripe credit card info
  Monitor how efficient cashiers are inputting orders and delivering orders to the kitchen
  Monitor the process for Snabb delivery or another 3rd party delivery service; and resolve any systematic issues;
User Interviews & Feedback:
  User interview delivery drivers on UI feedback conducted daily after product usage
Days : 10-14
Projected Date: Nov. 1 - 4
Notes: *Purposely skipping busy Halloween weekend

## Slide 5: Phase 4: Integrated Full Suite Test
Users:
  Anyone with invitation through referral code
Features Tested:
  Full suite test
  Referral code/discount
Process:
  Kitchen & delivery team to process orders independently
  Orders come in on a rolling basis
User Interviews & Feedback:
User interview with sample user group based and select kitchen staff
Days : 15-20
Projected Date: Nov. 5-10
Notes: If we feel extremely confident at this stage, we can cut the testing time for this phase and start rolling out the marketing promotional plan earlier.